## S1
Task# | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | User Management | 1.01 | Account Authentication | Frontend: Develop form for user login credentials | 2024-03-12 | 2024-04-09 | 100% | Somil
2 | User Management | 1.01 | Account Authentication | Backend: Implement logic to validate username/email and password against stored credentials (hashed and salted) | 2024-03-13 | 2024-04-09 | 100% | Vineet
3 | User Management | 1.01 | Account Authentication | Testing: Conduct unit tests to ensure secure user login functionality | 2024-03-14 | 2024-04-09 | 100% | Babu Ram Prakash
4 | User Management | 1.02 | Account Summary | Frontend: Design API endpoints for specific user data access (e.g., /api/users/me) | 2024-03-15 | 2024-04-09 | 100% | Gauri
5 | User Management | 1.02 | Account Summary | Backend: Implement logic to authenticate user requests and authorize access to data | 2024-03-16 | 2024-04-09 | 100% | Pranit
6 | User Management | 1.02 | Account Summary | Testing: Perform integration tests for retrieving user profile information | 2024-03-17 | 2024-04-09 | 100% | Varsha
7 | User Management | 1.03 | Customer Support | Frontend: Choose and integrate a ticketing system API or library | 2024-03-18 | 2024-04-09 | 100% | Sakshi
8 | User Management | 1.03 | Customer Support | Backend: Develop functionalities to create new tickets for user inquiries | 2024-03-19 | 2024-04-09 | 100% | Sharath
9 | User Management | 1.03 | Customer Support | Testing: Conduct end-to-end tests for ticket creation and management system integration | 2024-03-20 | 2024-04-09 | 100% | Honghao
10 | Product Discovery | 2.01 | Search Functionality | Frontend: Design and implement a search engine for clothes and shoes based on user queries | 2024-03-21 | 2024-04-09 | 100% | Somil
11 | Product Discovery | 2.01 | Search Functionality | Backend: Develop functionalities to parse and understand user search terms | 2024-03-22 | 2024-04-09 | 100% | Vineet
12 | Product Discovery | 2.01 | Search Functionality | Backend: Integrate with database to search for relevant product data based on keywords, filters, and other criteria | 2024-03-23 | 2024-04-09 | 100% | Babu Ram Prakash
13 | Product Discovery | 2.01 | Search Functionality | Testing: Perform unit tests for search functionality | 2024-03-24 | 2024-04-09 | 100% | Gauri
14 | Product Discovery | 2.02 | Filtering Options | Frontend: Develop user interface elements for selecting filters (e.g., dropdown menus, checkboxes) | 2024-03-25 | 2024-04-09 | 100% | Pranit
15 | Product Discovery | 2.02 | Filtering Options | Backend: Implement filters for refining search results based on size, color, brand, price, etc. | 2024-03-26 | 2024-04-09 | 100% | Varsha
16 | Product Discovery | 2.02 | Filtering Options | Backend: Integrate user-selected filters into the search queries sent to the database | 2024-03-27 | 2024-04-09 | 100% | Sakshi
17 | Product Discovery | 2.02 | Filtering Options | Testing: Perform integration tests for filter functionalities | 2024-03-28 | 2024-04-09 | 100% | Sharath
18 | Product Discovery | 2.03 | Personalized Recommendations | Backend: Develop algorithms to analyze user data and identify patterns | 2024-03-29 | 2024-04-09 | 100% | Honghao
19 | Product Discovery | 2.03 | Personalized Recommendations | Backend: Implement functionalities to recommend products similar to those previously viewed or purchased | 2024-03-30 | 2024-04-09 | 100% | Somil
20 | Product Discovery | 2.03 | Personalized Recommendations | Testing: Conduct unit tests for personalized recommendation algorithms | 2024-03-31 | 2024-04-09 | 100% | Varsha

## S2
Task# | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | Product Discovery | 2.04 | Trending Items | Frontend: Design user interface elements to showcase trending items | 2024-03-30 | 2024-04-09 | 100% | Pranit
2 | Product Discovery | 2.04 | Trending Items | Database: Implement logic to identify popular clothing and shoes based on sales data or user interactions | 2024-03-30 | 2024-04-09 | 100% | Varsha
3 | Product Discovery | 2.04 | Trending Items | Testing: Develop functionalities to collect and analyze data on product views, purchases, and user engagement | 2024-03-30 | 2024-04-09 | 100% | Anirudh
4 | Product Discovery | 2.04 | Trending Items | Frontend: Develop a dedicated section on the homepage or product listing pages to showcase trending items | 2024-03-31 | 2024-04-09 | 100% | Ram Prakash
5 | Product Discovery | 2.04 | Trending Items | Frontend: Develop algorithms or manual selection processes to identify featured items | 2024-03-31 | 2024-04-09 | 100% | Honghao
6 | Product Discovery | 2.05 | Featured Items | Frontend: Implement functionalities to display featured items prominently on the homepage or product listing pages | 2024-03-31 | 2024-04-09 | 100% | Sharath
7 | Product Discovery | 2.05 | Featured Items | Frontend: Design layouts and user interface elements to showcase featured items with clear visuals and calls to action | 2024-04-01 | 2024-04-09 | 100% | Siva Sai
8 | Product Discovery | 2.05 | Featured Items | Testing: Integrate with A/B testing tools to optimize the effectiveness of featured item placement and presentation | 2024-04-01 | 2024-04-09 | 100% | Gauri
9 | Product Discovery | 2.05 | Featured Items | Testing: Implement image resizing and compression techniques to optimize for web performance | 2024-04-02 | 2024-04-09 | 100% | Pranit
10 | Item Listing | 3.01 | Product Creation Forms | Frontend: Design user-friendly forms for adding new clothes and shoes | 2024-04-03 | 2024-04-09 | 100% | Ram Prakash
11 | Item Listing | 3.01 | Product Creation Forms | Database: Integrate with inventory management systems to track stock levels | 2024-04-04 | 2024-04-09 | 100% | Honghao
12 | Item Listing | 3.01 | Product Creation Forms | Frontend: Develop a rich text editor or similar functionality for creating detailed product descriptions | 2024-04-05 | 2024-04-09 | 100% | Somil
13 | Item Listing | 3.02 | Product Descriptions | Frontend: Implement features for formatting text, including bullet points, headings, and bolding | 2024-04-06 | 2024-04-09 | 100% | Somil
14 | Item Listing | 3.02 | Product Descriptions | Frontend: Implement features for formatting text, including bullet points, headings, and bolding | 2024-04-07 | 2024-04-09 | 100% | Varsha
15 | Item Listing | 3.03 | Images and Multimedia Attachments | Frontend: Develop functionalities for uploading high-resolution product images from various sources | 2024-04-08 | 2024-04-09 | 100% | Pranit
16 | Item Listing | 3.03 | Images and Multimedia Attachments | Frontend: Implement image resizing and compression techniques to optimize for web performance | 2024-04-09 | 2024-04-09 | 100% | Gauri
17 | Transaction Management | 4.01 | Payment Gateway Integration | Frontend: Integrate payment gateway UI elements into checkout process | 2024-04-09 | 2024-04-09 | 100% | Honghao
18 | Transaction Management | 4.01 | Payment Gateway Integration | Database: Set up tables to store transaction details and integrate with existing user data | 2024-04-09 | 2024-04-09 | 100% | Ram Prakash
19 | Transaction Management | 4.01 | Payment Gateway Integration | Testing: Conduct unit tests to ensure seamless integration of payment gateway APIs | 2024-04-09 | 2024-04-09 | 100% | Rohith

## S3
Task# | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | Transaction Management | 4.02 | Refunds and Returns Processing | Frontend: Develop UI components for initiating refunds and returns | 2024-04-09 | 2024-05-07 | 55 | Varsha
2 | Transaction Management | 4.02 | Refunds and Returns Processing | Backend: Implement business logic to process refund and return requests | 2024-04-10 | 2024-05-07 | 65 | Sakshi
3 | Transaction Management | 4.02 | Refunds and Returns Processing | Testing: Conduct unit tests for refund and return processing functionality | 2024-04-11 | 2024-05-07 | 50 | Pranit
4 | Transaction Management | 4.03 | Order Confirmation | Frontend: Design confirmation messages for successful orders | 2024-04-12 | 2024-05-07 | 55 | Gauri
5 | Transaction Management | 4.03 | Order Confirmation | Backend: Implement logic to generate order confirmation emails | 2024-04-13 | 2024-05-07 | 50 | Somil
6 | Transaction Management | 4.03 | Order Confirmation | Testing: Perform integration tests for order confirmation functionalities | 2024-04-14 | 2024-05-07 | 70 | Honghao
7 | Transaction Management | 4.04 | Order Status Tracking | Frontend: Develop UI components for tracking order status | 2024-04-15 | 2024-05-07 | 60 | Ram Prakash
8 | Transaction Management | 4.04 | Order Status Tracking | Backend: Implement APIs to provide real-time order status updates | 2024-04-16 | 2024-05-07 | 50 | Kalpana
9 | Transaction Management | 4.04 | Order Status Tracking | Testing: Conduct end-to-end tests for order status tracking functionalities | 2024-04-17 | 2024-05-07 | 50 | Nikhil
10 | User Experience and Security | 5.01 | Responsive User Interfaces | Frontend: Implement responsive design for user interfaces | 2024-04-18 | 2024-05-07 | 50 | Dhivya
11 | User Experience and Security | 5.01 | Responsive User Interfaces | Frontend: Optimize UI components for various screen sizes and devices | 2024-04-19 | 2024-05-07 | 50 | Vineet
12 | User Experience and Security | 5.01 | Responsive User Interfaces | Testing: Conduct cross-browser testing to ensure compatibility across browsers | 2024-04-20 | 2024-05-07 | 50 | Rohith
13 | User Experience and Security | 5.02 | Data Encryption | Frontend: Implement encryption algorithms for sensitive data protection | 2024-04-21 | 2024-05-07 | 50 | Siva Sai
14 | User Experience and Security | 5.02 | Data Encryption | Backend: Integrate encryption techniques for secure storage of user data | 2024-04-22 | 2024-05-07 | 30 | Sharath
15 | User Experience and Security | 5.02 | Data Encryption | Testing: Perform security audits to validate the effectiveness of data encryption | 2024-04-23 | 2024-05-07 | 30 | Anirudh
16 | User Experience and Security | 5.03 | Session Management | Frontend: Implement session management mechanisms for user authentication | 2024-04-24 | 2024-05-07 | 30 | Kunj Desh
17 | User Experience and Security | 5.03 | Session Management | Backend: Develop session handling logic to maintain user sessions securely | 2024-04-25 | 2024-05-07 | 30 | Gauri
18 | User Experience and Security | 5.03 | Session Management | Testing: Perform penetration testing to identify vulnerabilities in session management | 2024-04-26 | 2024-05-07 | 30 | Ram Prakash