## Sheet1
STYLE - X
APPLICATION MODULES | FEATURE BACKLOGS | STORY POINTS | SPRINT 1 | SPRINT 2 | SPRINT 3
|  |  | 2024-03-12 | 2024-04-09 | 2024-05-07
01. User Management | 01.01 Account Authentication | 5 | X
| 01.02 Account Summary | 3 | X
| 01.03 Customer Support | 5 | X
02. Product Discovery | 02.01 Search Functionality | 3 | X
| 02.02 Filtering options | 4 | X
| 02.03 Personalized Recommendations | 4 | X
| 02.04 Trending items | 4 |  | X
| 02.05 Featured Items | 3 |  | X
03. Item Listing | 03.01 Product Creation Forms | 5 |  | X
| 03.02 Product Descriptions | 3 |  | X
| 03.03 Images and Multimedia Attachments | 5 |  | X
04. Transaction Management | 04.01Payment Gateway Integration | 4 |  | X
| 04.02 Refunds and Returns Processing | 4 |  |  | X
| 04.03 Order Confirmation | 3 |  |  | X
| 04.04 Order Status Tracking | 3 |  |  | X
05. User Experience and Security | 05.01 Responsive User Interfaces | 4 |  |  | X
| 5.02 Data Encryption | 5 |  |  | X
| 05.03 Session Management | 5 |  |  | X
|  | VELOCITY: | 24 | 24 | 24